## KA2_SP_TIMELINE_TEMPLATE
Name of the project: | V.I.B.E Together
PROJECT TIMETABLE
|  | June July 2025 | August 2025 | September 2025 | October 2025 | November 2025 | December 2025 | January 2026 | February 2026 | March 2026 | April-May 2026 | June-July 2026 | August 2026 | September 2026 | M13 | M14
Project activity*
A1 |  | A1- Preparations for the project's Kick-Off Meeting - TPM 1 (ALL) A1.1- Corrdinators' Regular Meetings 1 (Online-ALL) A1.2- Informing all stakeholder about the project to collaborating with community organizations, and city councils and reaching a broad and diverse pool of potential volunteers. (ALL) A1.3 "Outreach Strategies" to select the most motivated and suitable candidates for the 4-month volunteering program (ALL): Step 1: Social Media & Collaborations -Platforms like FB, which have a significant older adult user base will be used to reach potential participants. (ALL) -Working with local senior centers, community organizations, and city councils will help identify and reach out to potential volunteers.(ALL) Step 2: The Preliminary Survey The Survey will be designed to select the most suitable volunteers from each organization by assessing key factors such as motivation, relevant experience, and alignment with the project's objectives, particularly in soft skills development for teenagers. The survey will evaluate candidates on their communication, teamwork, problem-solving, and empathy skills, essential for effectively volunteering in these areas. It will assess their ability to engage with teenagers, facilitate group activities, and handle challenges with empathy and insight."The Survey Questions and Evaluation Criteria" will be prepared by AUST. Volunteers who demonstrate strong skills in these areas, along with a genuine interest in mentoring and guiding teenagers, will be selected to participate, ensuring they can contribute meaningfully to the project's goals. (ALL) Step 3: Event Organization (Awereness Raising Campaign 1) "Volunteer Experience Day" will be organized, where interested participants can engage in a one-day mini-volunteering event. (ALL) Observers, including project coordinators and community leaders, will assess participants' enthusiasm, and engagement during these activities, helping to select the most motivated and suitable candidates for the 5-month volunteering program. (ALL) | A2.- Project's Website Developmet (TR) A2.1- Completing "GANNT CHART" to schedule all project-aligned activities. (IRE) A2.2- Dissemination the "Kick Off Meeting". (TR) *Newsletter 1: Summarizing the content, including project goals, timeline, and expectations or quotes from participantsg. (TR) *Updating the project's Website:Encouraging readers to visit the project website for more information and invite potential participants to join the project and participate in upcoming events. (TR) A2.3.- Local Meeting 1: Conducting a local meetinng to introduce the project goals, schedule, and expectations to selected volunteers from each partner organization. (ALL) STEPS: *Overviewing of the 18-month project timeline. *Detailed agenda for the 3-day training in AUSTRIA. *Explaining expectations for participants, including active involvement and regular "Digital Story Telling". *Setting up a communication channel (e.g., WhatsApp group) for ongoing support and updates. A2.4- Corrdinators' Regular Meetings 2 (Online-ALL) | A3.-The Wellbeing Assessment Survey & Evaluation (Pre) will be developed and applied to evaluate the wellbeing of selected volunteers before they begin their volunteering activities, midway through their participation, and at the end of the project. This will help to measure changes in their mental health, social engagement, and overall wellbeing over time. The Survey and Evaluation Tool will be prepared by taking into account these steps (AUST): Phase 1. Survey Development and Distribution (AUST) STEPS Defining Survey Objectives Identifying Specific Outcomes Designing the Survey Pilot Testing the Survey Adjusting the Survey Finalizing and Translating the Survey Distributing the Survey Phase 2. Data Analysis of the Survey (AUST) STEPS: Collecting and Organizing Data Analyzing Quantitative Data Calculating summary statistics for key variables Analyzing Qualitative Data Categorizing responses based on themes such as motivations for volunteering and perceived benefits. A3.1- "Mindfulness and Meditation Walks-Awereness Raising Campaign 2" to deepen mental and emotional awareness through mindfulness in nature. (ALL- Local Act.) A3.2- Corrdinators' Regular Meetings 3 (Online-ALL) | A4 - "Wellbeing and Active Aging Toolkit" (AUST) STEP 1 Foundation: Laying the Groundwork: Introduction to the core concepts of wellbeing and active aging, including definitions, initial strategies. (Note:The toolkit will develop progressively and evolve with the project) A4.1- Corrdinators' Regular Meetings 4 (Online-ALL) A4.2 .-Dissemination of the 1st Group Mobility of Adult Learners Page: *Social Media Accounts (During the Group Mobility of Adult Learners Page) (TR) Day 1: Posting highlights about the introduction session, including quotes and images of the discussions on the benefits of volunteering. Day 2: Sharing photos from the workshops with experienced volunteers, showcasing different volunteering opportunities. Day 3: Posting about the planning session, featuring participants creating their individual volunteering plans. *Volunteer Coordinators’ Reflections: Instead of a formal report, volunteer coordinators will write personal reflections on how the training inspired them to improve volunteer engagement in their local communities. This would focus on practical insights gained and potential strategies to implement. (ALL) *Newsletter 2: Including a section dedicated to the 5-day training in the next monthly newsletter. Providing a detailed overview of the training, participant experiences, and initial outcomes.Including links to the blog posts for readers who want more in-depth information. (TR) *Website- Group Mobility of Adult Learners Page: Creating a page on the project's website for the 3-day training. Including an overview, daily summaries, participant testimonials, photos, and links to the blog posts, newsletters, and social media updates and add downloadable resources, such as the presentation slides from the training, workshop materials, and the leaflet. (TR) A4.3-Digital Storytelling Workshop:Volunteer Coordinators that join the Group Mobility of Adult Learners (they will join this workshop in Group Mobility of Adult Learners by Türkiye) will arrange workshop in their countries for the volunteers that can't join the mobility. Thye will help them how to create and share personal stories using digital tools, integrating their volunteer experiences, personal journeys, or reflections on active aging and wellbeing.(ALL) | A5.- Volunteering Kick-off: Participants return to their countries, meet other volunteers and share their Volunteer Plans for 5 months created in the 1st Group Mobility of Adult Learners with their peers. (The templates created in the mobility will be revised and adjusted again according to the needs&potentials of each partner group) (ALL) A5.1-Volunteers in each organization start their volunteering at Local Schools and Youth Centers. Volunteer Coordinators in each partner organization provides participants ongoing guidance and support in every two weeks) (ALL) Volunteer Roles must cover: Communication:Through interactive workshops, guiding teenagers in mastering effective communication, including both verbal and non-verbal skills. Teamwork:By leading team-building exercises,teaching teenagers the principles of teamwork and emphasizing cooperation and conflict resolution. Emphathy:Through role-playing and reflective activities,encouraging youth to understand and relate to others' perspectives and emotions. Problemsolving:Facilitating workshops on problem-solving, equipping teenagers with critical thinking skills and creative strategies for overcoming challenges, and making informed decisions. A5.2-Digital Storytelling Toolkit: It will help volunteers create, share, and reflect on their experiences through digital storytelling. This toolkit will be prepared by Türkiye after the 1st mobility, drawing on the knowledge and insights gained during the session.It will also provide a platform for participants to share their personal and volunteering experiences creatively. (TURKIYE) A5.3"Wellbeing and Active Aging Toolkit" (AUST) STEP 2 Engaging the Mind and Body: Practical methods and exercises to engage participants in activities that enhance both mental and physical health. A5.4- Interpersonal Skills in Volunteering: Communication, Empathy, and Conflict Resolution - Webinar 1 (IRE): This webinar will cover essential interpersonal skills that enhance the volunteer experience, including active listening, empathy, teamwork, and managing conflicts. A5.5-Corrdinators' Regular Meetings 5 | A6.- Webinar 2: INTERNATIONAL VOLUNTEER DAY : The partners (coordinators,volunteers,welbeing experts etc.) will celebrate 5 December (IRE) A6.1- Digital Story Telling 1: Participants document their volunteer experiences, challenges, and achievements in monthly stories. (ALL) Steps: 1-Monthly Story Submissions:Participants write and submit their stories by the end of each month, including sections on experiences, challenges, achievements, and reflections. (ALL) 2-Story Review and Feedback:The coordinators review the submitted stories and provide feedback and encouragement to participants. (ALL) 3-Story Sharing:Publishing selected stories on the project website and social media platforms. (TR) 4-Feature participant stories in the project Newsletter 3. (TR) A6.2- Volunteer Coordinators guidance and support activities for volunteers: The volunteers and volunteer coordinators meet in each partner country (ALL) A6.3--Disseminating project aligned activies (local activities,volunteering,webinars) through project's social media account (FB,Instagram),blog posts from by participants and project coordinators, project's website updates. (every month-TR) | A7-Participants go on their volunteer roles. A7.1-Digital Story Telling 2: Participants document their experiences, challenges, and achievements in monthly stories. (ALL) A7.2-Disseminating project aligned activies (local activities,volunteering,webinars) through project's social media account (FB,Instagram),blog posts from by participanta and project coordinators, project's website updates. (every month- TR). A7.3- Healthy Aging and Wellbeing Seminar (Local Meeting 2) : Tips and practices for maintaining physical, mental, and emotional health as an older adult volunteer. (ALL) A7.4-"Wellbeing and Active Aging Toolkit" (AUST) STEP 3 Building Connections:Strategies to foster social connections and community engagement, emphasizing the importance of social wellbeing in active aging . A7.5- Volunteer Coordinators guidance and support activies for volunteers (ALL) | A8 -Participants go on their volunteer roles. A8.1-Digital Story Telling 3: Participants document their experiences, challenges, and achievements in monthly stories. (ALL) A8.2- The Wellbeing Assessment Survey & Evaluation (Midway) to assess and monitor the mentall, and emotional well-being of the volunteers throughout the project. (AUST) A8.3- Corrdinators' Regular Meetings 6 (ALL) A8.4- Volunteer Coordinators guidance and support activities for volunteers. (ALL) A8.5-Webinar 3:"Leadership and Mentorship in Volunteering: How to Inspire and Guide Others (Volunteer Coordinators from each partner country will join this webinar) : Equipping experienced volunteer coordinators with leadership skills to mentor volunteers. Topics will include leadership styles, team-building strategies, and mentoring techniques. (IRE) | A9 -Participants go on their volunteer roles. A9.1-Digital Story Telling 4: Participants document their experiences, challenges, and achievements in monthly stories. (ALL) A9.2- Webinar 3-Personal Growth through Volunteering : Exploring personal development opportunities, skill enhancement, and mental health benefits from volunteering. (IRE) A9.3- Corrdinators' Regular Meetings 7 (ALL) A9.4- Volunteer Coordinators guidance and support for volunteers. (ALL) | A10.- Finalizing Volunteering Roles. A10.1- Participants prepare short films that summarize their 5-month-volunteer roles to make them ready for the 2nd Group Mobility of Adults Learners (ALL) A10.2-"Wellbeing and Active Aging Toolkit" (AUST) STEP 4 Strengthening Resilience :Tools and techniques to build mental and emotional resilience, helping participants to navigate the challenges of aging. A10.3-Webinar 4: "Sustainable Volunteering: Creating Long-Term Change : Discussing strategies for sustainable volunteering that leave lasting effects on communities and individuals. Topics might include how to set up sustainable projects, (IRE) A10.4 - Intergenerational Volunteering Week (Local Awereness Raising Campaign 3) : Joint volunteering events where older and younger participants work together on community projects A10.5 - Corrdinators' Regular Meetings 8 A10.6- Volunteer Coordinators guidance and support for volunteers (ALL) | A11- Dissemination of the 2nd Group Mobility of Adults learners: *Social Media Accounts (During the 2nd LTT) (TR) Day 1: Posting highlights about the introduction session, including quotes and images of the discussions on the benefits of volunteering. Day 2: Sharing photos from the workshops with experienced volunteers, showcasing different volunteering opportunities. Day 3: Posting about the planning session, featuring participants creating their individual volunteering plans. *Coordinators’ Interviews with Participants: Coordinators could conduct short interviews with participants about their experiences, lessons learned, and how they plan to apply the skills in volunteering. These interviews can be shared on social media, newsletters, or the project website.(ALL) *Newsletter 5: Including a section dedicated to the 5-day training in the next monthly newsletter. Providing a detailed overview of the training, participant experiences, and initial outcomes.Including links to the blog posts for readers who want more in-depth information. (TR) *Website- Group Mobility of Adult Learners 2 Page: Creating a page on the project's website for the 3-day training. Including an overview, daily summaries, participant testimonials, photos, and links to the blog posts, newsletters, and social media updates and add downloadable resources, such as the presentation slides from the training, workshop materials, and the leaflet. (TR) 11.1-Art and Music Therapy Workshops ( Local Meeting 4) for emotional expression and mental healing. (ALL) A11.2 - Corrdinators' Regular Meetings 9 | A12.- The Wellbeing Assessment Survey & Evaluation (Post) to evaluate the overall impact of your project on participants' mental, and emotional health. (AUST). A12.1- Preparations for the project's Closure Meeting-TPM 2.(ALL) A12.2- Voices of Change : Creating and publishing Video Series that follows the journey of the volunteers from the beginning to the end of the project. This will include interviews, footage of the activities, and reflections on how the project has impacted their lives. (TR) A12.3-Wellbeing and Active Aging Toolkit" (AUST) STEP 5 Final Touches and Reflections: Reflection on the project journey, assessing outcomes, and planning for sustained wellbeing post-project. This phase should include final evaluations, personal stories, and strategies for continuing the practices learned throughout the project.(IRE) | A13.- Final Presentation of the project: Planing and organizing a festival to showcase the project outcomes and present the project's activities and celebrate participants' achievements.For general evaluation, an "Open-ended Questionnaire" will be applied to the festival participants (School and Youth Center Staff,Welbeing Specialists,Policy Makers,other NGO representatives) A13.1- Final Evaluation and Feedback: Conducting a final survey to the volunteers in each partner country and feedback session to assess the impact of the project. A13.2- Ongoing Support and Mentorship:Providing support through a network of mentors and planning for the sustainability of the project and future collaboration opportunities. A13.4.- Final Reporting and Dissemination:Compiling a comprehensive final report summarizing the project outcomes, lessons learned, and recommendations. A13.5- Disseminating the final report through the project website, newsletter, and social media.
M1 |  | July 2025 - THE PROJECT KICK-OFF Metting (1st TPM) in IRELAND | [9 empty] | July 2026- Closure Meeting (The 2nd TPM) in IRELAND
E1
C1 |  |  |  |  | October 2025 The 1st The 2nd Group Mobility of Adult Learners in AUSTRIA |  |  | Midterm Reflections: Virtual Mobility |  |  | April 2026 -The 2nd Group Mobility of Adult Learners in Türkiye
Please insert rows as needed
*Project activity types:
| An |  | - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On/An |  | - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn |  | - TRANSNATIONAL PROJECT MEETINGS
| En |  | - MULTIPLIER EVENTS
| Cn |  | - LEARNING/TEACHING/TRAINING ACTIVITIES
| n |  | - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.